## Sheet1
COMP376 Log
Meeting
Date | Artifact Type | Artifact Description | Cost (Hours) | Initials | Code
2012-09-24 | Meeting | Meeting to discuss project idea and proposal | 1 | CD | Documentation
2012-09-24 | Meeting | Meeting to discuss project idea and proposal | 1 | KA
2012-09-24 | Meeting | Meeting to discuss project idea and proposal | 1 | MT
2012-09-24 | Meeting | Meeting to discuss project idea and proposal | 1 | PM
2012-09-27 | Code | Create Repository | 0.1 | CD
2012-09-27 | Code | Create Empty XNA Project | 0.1 | CD
2012-09-27 | Documentation | Prepared presentation and game proposal templates. Also created work log. | 1 | KA
2012-10-01 | Documentation | Added sections to proposal document and proposal presentation | 0.25 | PM
2012-10-02 | Documentation | Added sections to proposal document and proposal presentation | 1 | KA
2012-10-03 | Documentation | Added sections to proposal document and proposal presentation | 0.5 | CD
2012-10-03 | Documentation | Added sections to proposal document and proposal presentation | 0.5 | MT
2012-10-04 | Documentation | Reviewed game proposal and presentation slides and submitted | 0.25 | KA
2012-10-15 | Meeting | Division of coding tasks and architecture discussion | 1 | CD
2012-10-15 | Meeting | Division of coding tasks and architecture discussion | 1 | KA
2012-10-15 | Meeting | Division of coding tasks and architecture discussion | 1 | MT
2012-10-15 | Meeting | Division of coding tasks and architecture discussion | 1 | PM
2012-10-17 | Code | Basic framework for how things will be inserted. | 2 | CD
2012-10-27 | Code | Added and worked on mini game LumberJack Bustle. Made changes to game framework removing and adding classes. | 5 | CD
2012-10-27 | Code | Worked on LumberJackBustle character class | 4 | MT
2012-10-27 | Code | Worked on mini game LumberJack Bustle Added content | 0.5 | PM
2012-10-28 | Code | Worked and made fixes on mini game LumberJack Bustle | 2 | CD
2012-10-28 | Code | Worked on LumberJackBustle character class | 4 | MT
2012-10-28 | Code | Worked on mini game LumberJack Bustle (Load Content & Player List) | 0.5 | PM
2012-10-29 | Code | Changed the resolution to be 720p. Worked and made fixes on mini game LumberJack Bustle | 5 | CD
2012-10-29 | Meeting | Meeting to discuss coding and progress presentation. (Lost power and wasn't present for last 15 mins.) | 1.25 | CD
2012-10-29 | Documentation | Created progress presentation outline and prepared for meeting | 1 | KA
2012-10-29 | Meeting | Meeting to discuss coding and progress presentation. | 1.5 | KA
2012-10-29 | Code | Worked on character class. Added content for different coloured knights. | 2 | MT
2012-10-29 | Meeting | Meeting to discuss coding and progress presentation. | 1.5 | MT
2012-10-29 | Code | Worked on mini game LumberJack Bustle (Draw) Added Camera | 2 | PM
2012-10-29 | Meeting | Meeting to discuss coding and progress presentation. | 1.5 | PM
2012-10-30 | Code | Made modifications/emergency fixes to framework. Worked on mini game LumberJack Bustle (collision) | 3 | CD
2012-10-30 | Code | Worked on content for instruction class and started coding | 4 | KA
2012-10-30 | Code | Worked on mini game LumberJack Bustle character class. | 1 | MT
2012-10-30 | Code | Worked on mini game LumberJack Bustle (Made lanes) Started Bumper Balls mini game and created under construction screen. | 4 | PM
2012-10-31 | Code | Worked on Lumberjack Bustle bugs and code (xbox controller logic) | 0.5 | CD
2012-10-31 | Code | Added content for instruction class Created instruction class for LumberJack Bustle and integrated it into main code. Added string table and Localisation Pipeline Created instruction class for bumper balls | 12 | KA
2012-10-31 | Code | Worked on Lumberjack Bustle bugs added sounds | 1 | MT
2012-10-31 | Code | Worked on Lumberjack Bustle bugs and code (added timer, game balancing, animations) Tested game on Xbox | 2 | PM
2012-11-01 | Code | Worked on Lumberjack Bustle (added songs | 0.1 | CD
2012-11-01 | Documentation | Added slides to progress presentation | 1 | CD
2012-11-01 | Documentation | Added slides to progress presentation, reviewed presentationa and submitted | 0.5 | KA
2012-11-01 | Documentation | Added slides to progress presentation | 0.5 | MT
2012-11-01 | Code | Worked on Lumberjack Bustle last minute fixes and animations (black hole) | 2 | PM
2012-11-01 | Documentation | Added slides to progress presentation | 0.25 | PM
2012-11-12 | Meeting | Meeting to split up tasks | 1.67 | CD
2012-11-12 | Meeting | Meeting to split up tasks | 1.67 | KA
2012-11-12 | Meeting | Meeting to split up tasks | 1.67 | MT
2012-11-12 | Code | Bumper Balls + Framework | 2 | PM
2012-11-12 | Meeting | Meeting to split up tasks | 1.67 | PM
2012-11-13 | Code | Bumper Balls | 3 | PM
2012-11-16 | Code | Finish Bumper Balls + test | 2 | PM
2012-11-23 | Documentation | Created game design document template | 1 | KA
2012-11-23 | Code | Fix team stuff in Bumper balls | 1 | PM
2012-11-24 | Documentation | Worked on game design document budget section | 1.5 | KA
2012-11-24 | Code | Work on Duel Mini Game | 3 | PM
2012-11-25 | Code | Worked on menu system and screenshots for preview | 5 | CD
2012-11-25 | Meeting | Meeting to show changes and discuss progress of coding and possible scoping. | 1 | CD
2012-11-25 | Code | Added scoring and made changes to instructions. | 12 | KA
2012-11-25 | Documentation | Updated game design document | 1 | KA
2012-11-25 | Meeting | Prepare for meeting | 0.5 | KA
2012-11-25 | Meeting | Meeting to show changes and discuss progress of coding and possible scoping. | 1 | KA
2012-11-25 | Code | Worked on Fireball Tactics | 8 | MT
2012-11-25 | Meeting | Showed work on Fireball Tactics | 1 | MT
2012-11-25 | Meeting | Meeting to show changes and discuss progress of coding and possible scoping. | 1 | PM
2012-11-26 | Code | Implemented choose menu fully, and main menu (with cursors). Fixed bugs. | 6 | CD
2012-11-26 | Code | Fixed a bug for all mini games where game over would not occur properly | 1 | CD
2012-11-26 | Code | Made changes to scoring and instructions. | 1 | KA
2012-11-26 | Code | Worked on score and instructions for fire tactics. | 2.5 | KA
2012-11-27 | Code | Implemented the story mode framework for Pat | 1 | CD
2012-11-27 | Code | Made teams depending on score for Duel and BB | 2 | PM
2012-11-28 | Code | Worked on scoring and instructions. | 1.5 | KA
2012-11-28 | Code | Added a firewall to FireballTactics and some other finishing touches | 3 | MT
2012-11-28 | Code | Fixing Bugs, Finishing FireBallTactics | 9 | PM
2012-11-28 | Code | Fixing Bugs, Adding Story + Credits | 5 | PM
2012-11-29 | Meeting | Final Meeting to prepare for demo and set up xbox | 3 | CD
2012-11-29 | Meeting | Final Meeting to prepare for demo and set up xbox | 3 | KA
2012-11-29 | Meeting | Final Meeting to prepare for demo and set up xbox | 3 | MT
2012-11-29 | Code | Last minute bug fixes | 1.5 | PM
2012-11-29 | Meeting | Final Meeting to prepare for demo and set up xbox | 3 | PM
2012-12-01 | Documentation | Updated documentation | 12.5 | KA
2012-12-03 | Documentation | Documentation for the game doc and review | 6 | CD
2012-12-03 | Code | Deployment | 1 | CD
2012-12-03 | Documentation | Reviewed Section 10 | 0.5 | KA
2012-12-03 | Documentation | Documentation for the game doc and review | 6 | MT
2012-12-03 | Documentation | Documentation for the game doc and review | 6 | PM
2012-12-03 | Documentation | Updated document and contributed budget. | 3 | KA
|  | TOTAL | 208.48 | h